## Working schedule
Reconcile a construction draw to approved work, retainage and budget changes
Completed hypothetical example — no actual transaction.
Published by Jaken Finance Group ¦ commercialdebtadvisory.com/templates/construction-draw-package-and-change-order-register/
Completed work is cumulative eligible value, not the current invoice total. Prior funded is cumulative for the same line.
Request = eligible completed work × (1 − retainage%) − prior funded under this hypothetical convention.
Actual eligibility, retainage, equity order and lien documentation follow the specific loan and professional review.
Blue = editable input. Black on gray = formula. Verify evidence, dates and contractual definitions before use.
budget line | original budget usd | approved changes usd | pending changes usd | approved budget usd | eligible completed work usd | retainage percent | prior funded usd | current request usd | support and open issue
Structure | 800000 | 50000 | 0 | 850000 | 500000 | 10 | 300000 | 150000 | Inspection and invoices required; approved change CO-1 included
Mechanical | 300000 | 0 | 20000 | 300000 | 300000 | 10 | 220000 | 50000 | CO-2 pending; $20,000 potential additional cost not approved or included in eligible work

## Instructions
Working instructions
Reconcile a construction draw to approved work, retainage and budget changes
Example status: Hypothetical illustration
Completed work is cumulative eligible value, not the current invoice total. Prior funded is cumulative for the same line.
Request = eligible completed work × (1 − retainage%) − prior funded under this hypothetical convention.
Actual eligibility, retainage, equity order and lien documentation follow the specific loan and professional review.
Amounts and dates use the units in the headers. Percent inputs are whole percentages unless stated otherwise.
Formula outputs are arithmetic checks; they do not establish eligibility, approval or contractual compliance.
When adding rows, extend formulas and validation. Preserve stable identifiers and source references.
Full field instructions and common errors: https://commercialdebtadvisory.com/templates/construction-draw-package-and-change-order-register/
Public contact: 833-264-7776 ¦ info@jakenfinancegroup.com